## Slide 1: Clothes ‘R’ Us Case Study Analysis
Mansi Bodke
Anushri Dixit Jay Mehta Fanil Gada Neeraj Subhedar Apurva Rawat

## Slide 2
Jan’02 | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
Nov | Dec | Jan
Feb
DEVELOPMENT | IMPLEMENT | PILOT
PLAN
Product Def and Arch | Requirements | Design | Code | Test | Initial Deployment
Contingency plan, Critical path defined, Cost control plan | A risk and issue log | Intermediate touch base meetings Collab with committee to design GUI | Risk log HRM | Avoided back and forth with vendor, provided immediate instruction for replacement | Training sessions for store managers
 |  | Ops steering committee sign off delayed | All 6 product managers left | incorrect hardware supplied by the vendor | ? | ?
?
 |  | four-week delay on the GUI sign-off | four-week delay on next phase | four-week delay on next phase | ? | ?
TIMELINE
PROJECT STAGE
OBSTACLE
IMPACT
MISSING
Project at a Glance

## Slide 3: CRU IT Staff
Chart: Planned vs Actual Burn
| 37257 | 37288 | 37316 | 37347 | 37377 | 37408 | 37438 | 37469 | 37500 | 37530
CRU IT Staff Planned | 192917 | 385834 | 578751 | 771668 | 964585 | 1157502 | 1350419 | 1543336
CRU IT Staff Actual Burn | 192917 | 385834 | 578751 | 771668 | 964585 | 1157502 | 1157502 | 1350419
Scheduled completion of Design phase
GUI Impact
Effects of GUI Impact

## Slide 4: CRU IT Staff
Chart: Planned vs Planned after Impact
| 37257 | 37288 | 37316 | 37347 | 37377 | 37408 | 37438 | 37469 | 37500
CRU IT Staff Planned | 192917 | 385834 | 578751 | 771668 | 964585 | 1157502 | 1350419
CRU IT Staff Planned after Impact | 192917 | 385834 | 578751 | 771668 | 964585 | 1157502 | 1157502 | 1350419 | 1350419
GUI Impact
Project Manager Impact
Effects on timeline

## Slide 5: CRU IT Staff – Proposed Baseline
Chart: Actual Baseline v/s New Baseline
| 37469 | 37500 | 37530 | 37561 | 37591 | 37622 | 37653 | 37681 | 37712 | 37742 | 37773 | 37803 | 37834
Actual Planned | 1543336 | 1736253 | 1929170 | 2122087 | 2315004 | 2507921 | 2700838 | 2789588 | 2878338
Planned after rebaselining | 1929170 | 2122087 | 2315004 | 2507921 | 2700838 | 2893755 | 3086672 | 3279589 | 3472506 | 3561256 | 3650006
Scheduled completion of Deployment phase
Scheduled completion with new baseline
WorldCom Bankruptcy
Incompatible OS

## Slide 6: ABC Consulting Staff
Chart: Planned vs Actual Burn
| 37257 | 37288 | 37316 | 37347 | 37377 | 37408 | 37438 | 37469
ABC Staff Planned | 379200 | 1384320 | 2389440 | 3506240 | 5271520 | 7821440 | 10427360 | 13073280
ABC Staff Actual Burn | 379200 | 1384320 | 2389440 | 3506240 | 5271520 | 7036800 | 9315040 | 11920960
Scheduled completion of Design phase
GUI Impact
Effects of GUI Impact

## Slide 7: ABC Consulting Staff
Chart: Planned vs Planned after Impact
| 37257 | 37288 | 37316 | 37347 | 37377 | 37408 | 37438 | 37469 | 37500 | 37530
ABC Staff Planned | 379200 | 1384320 | 2389440 | 3506240 | 5271520 | 7821440 | 10427360
ABC Staff Planned after Impact | 379200 | 1384320 | 2389440 | 3506240 | 5271520 | 7036800 | 7549760 | 10155680 | 10155680
GUI Impact
Project Manager Impact
Effects on timeline

## Slide 8: ABC Consulting Staff - Proposed Baseline
Chart: Actual Baseline v/s New Baseline
| 37469 | 37500 | 37530 | 37561 | 37591 | 37622 | 37653 | 37681 | 37712 | 37742 | 37773 | 37803 | 37834
Actual Planned | 13073280 | 15759200 | 18445120 | 21179040 | 23912960 | 25322720 | 25602720 | 25882720 | 26162720
Planned after rebaselining | 12801600 | 15487520 | 18173440 | 20859360 | 23593280 | 26327200 | 27664960 | 29074720 | 29354720 | 29634720 | 29914720
Scheduled completion of Deployment phase
Scheduled completion with new baseline
WorldCom Bankruptcy
Incompatible OS

## Slide 9
RISK No. | RISK DESCRIPTION | IMPACT on Success | LIKELIHOOD of occurrence | ACTION PLAN |  | IMPACT on Success |  | LIKELIHOOD of occurrence
HR/001 | Lack of motivation | High | Medium | Maintain performance tracker and check their productivity |  | High |  | High
TS/001 | Incompatibility of application with OS | High | High | Communicate the requirement accurately and maintain proper documentation |  | Medium |  | Medium
DP/001 | Delay from WorldCom for setting up private network | High | Medium |  |  | Low |  | Low
DV/001 | Serious issues might be faced by coding team | Medium | Low | Complete individual coding pieces and hand over to testing team |  |  |  | 
DS/001 | Incorrect understanding of scope and requirements | High | Low | Document the scope and requirements accurately and QA team to monitor every piece |  |  |  | 
DS/002 | GUI sign off from operations steering committee | High | Medium | Some slack in the timeline and submit the proposal before June |  |  |  | 
Tools and Methods to leverage
Risk Log
FMEA
MS Project

## Slide 10: Change Request
Stringent timelines gave no slack for any additional changes
However, numerous changes suggested by the Operations Steering Committee resulted in the project getting delayed by a month
A solid change management process can be a project manager's best friend

## Slide 11: Human Resource Management
History suggests that when employees believe that high efforts are often met with high rewards, they become more motivated
The components of such motivation are:
Increasing Compensation
Increasing Expectancy
Increasing Instrumentality
Increasing Valiance

## Slide 12: Contract-type Recommendation
Orlin should had made a Firm-Fixed-Price (FFP) contract with the hardware vender
FFP has minimum buyer risk
In FFP, the contractor is obliged to provide an acceptable deliverable at the time, place and price specified in the contract
A typical application of FFP is commercial supplies and services which is exactly the case here

## Slide 13: Proactive Management Approach
Steps to move from a reactive to proactive project management
  Take back control of time
  Look at process
  Understand and manage risks
  Focus on morale
  Build in continuous improvement

## Slide 14: Thank You!